## Sheet1
Phase # | Deliverable | Section of SOW | Est. Hours | Price | Assumptions/Constraints
Design, Develop and Implementation Phase 1 - Initiation
DDI 1-1 | Kick Off Meeting and Materials | Kick off for the project and review of the project management approach
DDI 1-2 | Project Management Plan | The Project Management plan for project execution, designed with input from AGFG
DDI 1-3 | Knowledge Transfer Plan | A plan of the ways AGFG staff will gain knowledge of the new system.
Design, Develop and Implementation Phase 2 - Requirements Elaboration and Design
DDI2-1 | User Guides | Details description of all discrete business process and how users will execute them in the new system.
DDI2-2 | Requirements Traceability Documentation | Requiremtns linked to configurations elements of the System, describing how the requirement is met.
DDI2-3 | File Import/Export Definitions | Documentation of File Layout and Mapping for system interfaces.
DDI2-4 | Custom Report Definitions | Detailed requirements for Custom Reports
DDI2-5 | Data Conversion Plan | A detailed plan for converting current data to a new system.
Design, Develop and Implementation Phase 3 - Execution
DDI3-1 | Data Dictionary | The Data layout of the new System documented in detail.
DDI3-2 | Data Conversion Exception Reports | Reporting of all errors to facilitate AGFG's data cleanup efforts.
Phase # | Deliverable | Section of SOW | Est. Hours | Price | Assumptions/Constraints
Design, Develop and Implementation Phase 4 - UAT
DDI4-1 | Master Test Plan | Overal Plan for testing the System prior to deployment.
DDI4-2 | Testing Results | Results of execution of Various testing objectives as described in the Master Test Plan.
Design, Develop and Implementation Phase 5 -Implementation
DDI5-1 | Go-Live Plan | Plan outling the steps needed to implement the system in Production
DDI5-2 | Training Plan | Plan for Providing all required training material.
DDI5-3 | Training Materials | Training materials customized to be specific to AGFG users as outlined in the training plan.
Design, Develop and Implementation - All Phases
DDI-1 | Weekly Status Reports | Weekly Status updates and meetings that follow the agreed upon schedule.
DDI-2 | Meeting Notes | Notes from meetings are delivered following the agreed upon schedule.
Optional Service Transition Costs
Phase # | Deliverable | Unit Cost | Quanity | Total Cost | Notes
ST-1 | Service Hours | 200 Hours per year used for training, development, and customization of the system. AGFG will determine annually if necessary
ST-2 | User Conference | Admission for 3 to all in person or virtual conferences and training vendors offers each year
Transaction or Variable Licensing Costs - Years 1 - 5
Phase # | Deliverable | Unit Cost | Quanity | Total Cost | Notes
OP-1 | Adjuster User License |  | 170 |  | If submitting Innovative pricing, fill out this pricing sheet and submit an additional page with the innovative pricing model. Innovative pricing includes caps, fixed fees, lower costs for certain user types etc.
OP-2 | Full User Licenses |  | 30
OP-3 | Hosting Cost |  | 1
OP-4 | Storage Cost |  | 1
OP-5 | Additional Annual Costs |  | 1
| How often are user license costs calculated? | Annualy, monthly, weekly or daily?
|  | Total Annual Operational Cost |  | 0
|  | Total Implementation Cost |  | 0